## Best
| Network Problem | [5 empty] | Project start: | [7 empty] | 2024-10-20
| MSDS460 | Timmy Li |  |  |  |  | Display week: | [7 empty] | 1
SIMPLE GANTT CHART by Vertex42.com
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | [5 empty] | 2024-10-21 | [6 empty] | 2024-10-28 | [6 empty] | 2024-11-04 | [6 empty] | 2024-11-11 | [6 empty] | 2024-11-18 | [6 empty] | 2024-11-25 | [6 empty] | 2024-12-02 | [6 empty] | 2024-12-09
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2024-10-21 to 2024-12-15
 | time axis 2024-10-21 to 2024-12-15
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Initiation
| Describe product A | PM | 100% | 2024-10-20 | 2024-10-21 | 2
| Develop Marketing Strategy B | PM | 100% | 2024-10-20 | 2024-10-22 | 3
| Design Brochure C | PM | 100% | 2024-10-22 | 2024-10-24 | 3
Planning and design
| Requirements Analysis D1 | PM | 100% | 2024-10-22 | 2024-10-25 | 4
| Software Design D2 | BD and FD | 100% | 2024-10-26 | 2024-10-31 | 6
| System Design D3 | BD and DE | 100% | 2024-10-26 | 2024-10-31 | 6
| Coding D4 | FD AND BD | 100% | 2024-11-01 | 2024-11-11 | 11
| Write Documentation D5 | PM and Devs | 100% | 2024-11-12 | 2024-11-14
| Unit Testing D6 | FD AND BD | 100% | 2024-11-12 | 2024-11-15
| System Testing D7 | DE and BD | 100% | 2024-11-16 | 2024-11-20
| Package Deliverables D8 | PM | 100% | 2024-11-21 | 2024-11-23 | 3
Execution
| Survey potential Market E | PM | 100% | 2024-10-24 | 2024-10-27 | 4
| Develop Pricing Plan F | PM | 100% | 2024-11-24 | 2024-11-26 | 3
| Develop implementation plan G | PM | 100% | 2024-11-24 | 2024-11-28 | 5
| Write client proposal H | PM | 100% | 2024-11-29 | 2024-12-01 | 3
Insert new rows ABOVE this one
Formulas:
Display week: = [Display week:, row below]

## Expected
| Network Problem | [5 empty] | Project start: | [7 empty] | 2024-10-20
| MSDS460 | Timmy Li |  |  |  |  | Display week: | [7 empty] | 1
SIMPLE GANTT CHART by Vertex42.com
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | [5 empty] | 2024-10-21 | [6 empty] | 2024-10-28 | [6 empty] | 2024-11-04 | [6 empty] | 2024-11-11 | [6 empty] | 2024-11-18 | [6 empty] | 2024-11-25 | [6 empty] | 2024-12-02 | [6 empty] | 2024-12-09
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2024-10-21 to 2024-12-15
 | time axis 2024-10-21 to 2024-12-15
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Initiation
| Describe product A | PM | 100% | 2024-10-20 | 2024-10-22 | 3
| Develop Marketing Strategy B | PM | 100% | 2024-10-20 | 2024-10-23 | 4
| Design Brochure C | PM | 100% | 2024-10-23 | 2024-10-26 | 4
Planning and design
| Requirements Analysis D1 | PM | 100% | 2024-10-23 | 2024-10-27 | 5
| Software Design D2 | BD and FD | 100% | 2024-10-28 | 2024-11-04 | 8
| System Design D3 | BD and DE | 100% | 2024-10-28 | 2024-11-07 | 11
| Coding D4 | FD AND BD | 100% | 2024-11-08 | 2024-11-23 | 16
| Write Documentation D5 | PM and Devs | 100% | 2024-11-24 | 2024-11-27
| Unit Testing D6 | FD AND BD | 100% | 2024-11-24 | 2024-11-29
| System Testing D7 | DE and BD | 100% | 2024-11-30 | 2024-12-07
| Package Deliverables D8 | PM | 100% | 2024-12-08 | 2024-12-11 | 4
Execution
| Survey potential Market E | PM | 100% | 2024-10-26 | 2024-10-31 | 6
| Develop Pricing Plan F | PM | 100% | 2024-12-12 | 2024-12-15 | 4
| Develop implementation plan G | PM | 100% | 2024-12-12 | 2024-12-17 | 6
| Write client proposal H | PM | 100% | 2024-12-18 | 2024-12-21 | 4
Insert new rows ABOVE this one
Formulas:
Display week: = [Display week:, row below]

## Worst
| Network Problem | [5 empty] | Project start: | [7 empty] | 2024-10-20
| MSDS460 | Timmy Li |  |  |  |  | Display week: | [7 empty] | 1
SIMPLE GANTT CHART by Vertex42.com
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | [5 empty] | 2024-10-21 | [6 empty] | 2024-10-28 | [6 empty] | 2024-11-04 | [6 empty] | 2024-11-11 | [6 empty] | 2024-11-18 | [6 empty] | 2024-11-25 | [6 empty] | 2024-12-02 | [6 empty] | 2024-12-09
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2024-10-21 to 2024-12-15
 | time axis 2024-10-21 to 2024-12-15
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Initiation
| Describe product A | PM | 100% | 2024-10-20 | 2024-10-23 | 4
| Develop Marketing Strategy B | PM | 100% | 2024-10-20 | 2024-10-24 | 5
| Design Brochure C | PM | 100% | 2024-10-24 | 2024-10-28 | 5
Planning and design
| Requirements Analysis D1 | PM | 100% | 2024-10-24 | 2024-10-30 | 7
| Software Design D2 | BD and FD | 100% | 2024-10-31 | 2024-11-10 | 11
| System Design D3 | BD and DE | 100% | 2024-10-31 | 2024-11-20 | 21
| Coding D4 | FD AND BD | 100% | 2024-11-21 | 2024-12-11 | 21
| Write Documentation D5 | PM and Devs | 100% | 2024-12-12 | 2024-12-16
| Unit Testing D6 | FD AND BD | 100% | 2024-12-12 | 2024-12-18
| System Testing D7 | DE and BD | 100% | 2024-12-19 | 2024-12-27
| Package Deliverables D8 | PM | 100% | 2024-12-28 | 2025-01-01 | 5
Execution
| Survey potential Market E | PM | 100% | 2024-10-28 | 2024-11-03 | 7
| Develop Pricing Plan F | PM | 100% | 2025-01-02 | 2025-01-06 | 5
| Develop implementation plan G | PM | 100% | 2025-01-02 | 2025-01-08 | 7
| Write client proposal H | PM | 100% | 2025-01-09 | 2025-01-13 | 5
Insert new rows ABOVE this one
Formulas:
Display week: = [Display week:, row below]

## Sheet1
taskID | task | predecessorTaskIDs | bestCaseHours | expectedHours | worstCaseHours | projectManager(me) | frontendDeveloper | backendDeveloper | dataScientist(me) | dataEngineer
A | Describe product (PM) |  | 8 | 16 | 24
B | Develop marketing strategy (PM) |  | 16 | 24 | 32
C | Design brochure (PM or FD) | A | 16 | 24 | 32
D | Develop product prototype |  | 272 | 432 | 544
D1 | Requirements analysis (PM) | A | 24 | 32 | 48
D2 | Software design(BD and FD) | D1 | 40 | 56 | 80
D3 | System design(BD and DE) | D1 | 40 | 80 | 160
D4 | Coding(FD and BD) | D2, D3 | 80 | 120 | 160
D5 | Write documentation(PM and Devs) | D4 | 16 | 24 | 32
D6 | Unit testing (FD and BD) | D4 | 24 | 40 | 48
D7 | System testing (DE and BD) | D6 | 32 | 56 | 64
D8 | Package deliverables (PM) | D5, D7 | 16 | 24 | 32
E | Survey potential market (PM) | B, C | 24 | 40 | 48
F | Develop pricing plan (PM) | D8, E | 16 | 24 | 32
G | Develop implementation plan (PM) | A, D8 | 24 | 40 | 48
H | Write client proposal (PM) | F, G | 16 | 24 | 32
|  |  | 392 | 624 | 872